## SPD TrackerSheet OP Ultra Pro M
| DRIVE LINK: | https://drive.google.com/drive/folders/1BGo6AqK4cpCNNiin8GcbS-wJXfz7NBsn?usp=sharing |  | APP LINK: | CID Web-app Link
Group/Phase | Task ID | Task Description | Assigned To | Est. Days | Start Date | End Date | Status
Phase 1: Setup & Data Preparation | 1.1 | Project Environment Setup (Git Repository, Virtual Environment, Dependency List) | Sarvagya | 1 | 2025-11-06 | 2025-11-06 | Done
Phase 1: Setup & Data Preparation | 1.2 | Data Acquisition & Initial EDA (Handle missing values, understand feature types, initial anomaly exploration) | Pritish | 2 | 2025-11-06 | 2025-11-07 | Done
Phase 1: Setup & Data Preparation | 1.3 | Data Preprocessing (One-Hot/Label Encoding, Feature Scaling/Normalization) & Feature Engineering | Daksh | 3 | 2025-11-08 | 2025-11-10 | Done
Phase 1: Setup & Data Preparation | 1.4 | Final Data Split (Train/Validation/Test) and create initial data loading utility functions. | Sarvagya | 1 | 2025-11-10 | 2025-11-10 | Done
Phase 2: Model Training & Selection | 2.1 | Train Ensemble & Boosting Models (Random Forest, XGBoost, CatBoost, LightGBM) | Daksh | 3 | 2025-11-11 | 2025-11-13 | Done
Phase 2: Model Training & Selection | 2.2 | Train Classic ML Models (Decision Tree, Logistic Regression, KNN, Gaussian Naive Bayes) | Pritish | 3 | 2025-11-11 | 2025-11-13 | Done
Phase 2: Model Training & Selection | 2.3 | Model Evaluation & Selection (Consolidate results, select Top 2 based on F1-Score/ROC-AUC, save best models using 'pickle'/'joblib') | Sarvagya | 2 | 2025-11-14 | 2025-11-15 | Done
Phase 2: Model Training & Selection | 2.4 | Hyperparameter Optimization for Top 2 Models (Grid Search or Bayesian Optimization) | Daksh | 3 | 2025-11-16 | 2025-11-18 | Done
Phase 3: Dashboard & Integration | 3.1 | Backend API Setup (Create prediction function, model loading pipeline, pre-prediction data transformation) | Pritish | 3 | 2025-11-19 | 2025-11-21 | Done
Phase 3: Dashboard & Integration | 3.2 | Streamlit UI Development (Design dashboard layout, implement prediction input form and result display) | Sarvagya | 4 | 2025-11-19 | 2025-11-22 | Done
Phase 3: Dashboard & Integration | 3.3 | Implement Metrics & Visualization in Dashboard (Display metrics, Confusion Matrix plots, feature importance) | Daksh | 3 | 2025-11-23 | 2025-11-25 | Done
Phase 3: Dashboard & Integration | 3.4 | Integration Testing: Ensure seamless connection between Streamlit Frontend and ML Backend (End-to-end functionality) | Pritish | 3 | 2025-11-23 | 2025-11-25 | Done
Phase 4: Testing & Finalization | 4.1 | Comprehensive System Testing & Security Review (Test detection accuracy, edge cases, model drift potential) | Sarvagya | 3 | 2025-11-26 | 2025-11-28 | Done
Phase 4: Testing & Finalization | 4.2 | Final Project Documentation & Presentation Prep (README, User Guide, key findings summary) | Pritish | 3 | 2025-11-26 | 2025-11-28 | Done
Phase 4: Testing & Finalization | 4.3 | Final Review, Code Refactoring, and Repository Handover (Cleanup unused code, ensure all files are complete) | All | 3 | 2025-11-29 | 2025-12-01 | Done